## Project plan
| wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12
Define backend data tables | bar: wk1
Create homepage, logo, FB integration/Linked In integration | bar: wk2
Create an app that can register users and add their name in our database | bar: wk3
Use those sample names and find out how we can have them agree to disclosing their location real time and have an option of hiding their location as and when they want | bar: wk4 to wk5
Then we should use sample 5-6 users and find out how it shows on a map (moving dots) | bar: wk5
Need to sync iMessage or text seamlessly connect to our app so ppl can use that for messaging | bar: wk6 to wk7
Need some way to confirm request to pick up. | bar: wk8 to wk9
Rating system | bar: wk10
Payment system (paypal/credit card) | bar: wk11
Also need to dig up the database that shows plausible stopping locations. | wk12: Stretch goal

## Database structure
User | Car | Reservation | Reviews
User ID | Vehicle number plate | User ID | Review ID
First name | VIN (optional) | Reservation ID | Review Text
Last name | Model | Vehicle number plate | User ID
Nick Name | Make |  | Route ID
Password | Color
Address (optional) | Type
Zipcode (optional) | User ID
Vehicle number plate
Vehicle state
Contact number
Email ID
Gender
Rating
FB ID (Can be used by the user to avoid entering all the information again)

## Other details
How will we match supply - demand.
What if one of the parties don't show up. What's the cancellation policy?
Will it be pre-paid or post-paid?
How will the payment happen?

## Rating algo
We will have stars that will prompt user to click on it and rate. When the user clicks on a star, let’s say star number 4, the weight 4 will be converted to a new heavier magnitude. We want to do this because with the small range 1 through 5 we cannot manipulate the info. Assigning different magnitudes to different weights will increase the range.
So, for example we will assign 50 to 5, 40 to 4 and so on. Hence if we take the average now, there will be more range difference between two numbers and we can depict that better on the strength meter. And there will be a greater difference in the cumulative average as compared to when the weights were just 4 and 5. It is better depicted on a strength meter.
I think rating out of 5 or 50 is the same thing. I understand the weights but if you are going to keep it linear, then it won't make any difference other than the fact that 4 will be seen as 40 and 5 as 50.

## Processes
Ride - Person who will have the car
Rider - Person who is looking for the car
RED implies that there is an algo for this step
Algorithms needed:
Step number | Step description | Details
0 | Purchase domain name | Ridesynth.com | Purchased
1 | Getting user to our website | -Ads on FB -Ads on rental car sites -iAds within iPhone apps and android apps |  | Top raters should show up top in rider's search
Pricing of ride - based on gas amount + insurance + our fee
2 | Landing page | -Something similar to your sample page, simple and clean -user login name -password -FB integration logo |  | Payment options - cash, credit card, online payment, bank to bank, user can load money to his "RideSynth" account and money will be deducted based on pricing algo
Potential rides for future date and time
3 | Sign in - FB integration | -User info or FB link
4 | Locate your route | -User will enter zipcode Ex. 94086 -User can enter starting point referencing cross streets. Ex: El camino and Castro -User can enter ending point referencing cross streets. Ex: El camino and Castro
5 | Find carpooling options | User will have a choice of leaving now vs. later. Something like we have in google maps. Input will be "departure time" or "find me a ride now"
|  | Real time pooling -Above inputs will show moving dots for people who had offerred to pick up a ride - Red dot for people who don't have a room in their car, Green dot for those who have a room in their car - User can hover the mouse or touch the dot and it will give car info, ride's info, ride's rating | Ahead of time pooling -User will enter departure time and date -This search will take rider to the page with all potential rides -Rider will select the appropriate ride by looking at FB profile (if public), LinkedIn profile (if public), rating
6 | Request sending from Rider to Ride | Real time pooling -Once the rider decides on ride, he clicks on the moving dot | Ahead of time pooling -User will enter departure time and date -This search will take rider to the page with all potential rides -Rider will select the appropriate ride by looking at FB profile (if public), LinkedIn profile (if public), rating
7 | Request approval
8 | Request confirmation
9 | Request decline
10 | Showing that the car has no space or has a space